## Dashboard
Project Name: Plant pal project
Description: This is a new project launched by Green Pal
Owner: A. Bhowmick
Status: Draft
Key Docs | Description
Project charter | This is the synopsis of the project. Link - https://github.com/bhaumikananda/GoogleProjectManagement/blob/main/AB_Project-charter.docx
Statement of work | The statement of work for the plant pal project. Link - https://github.com/bhaumikananda/GoogleProjectManagement/blob/main/ProjectGreen-SOW.docx
Risk management plan | This document is to maintain all the risks and its corresponding mitigation plan. Link - https://github.com/bhaumikananda/GoogleProjectManagement/blob/main/Activity-Template_-Risk-management-plan.docx
Schedule | This document will have the details of the schedule of the program. Link - https://github.com/bhaumikananda/GoogleProjectManagement/blob/main/AB_Activity-Template_-Gantt-chart.xlsx
Budget | The financials and cost details. Link - https://github.com/bhaumikananda/GoogleProjectManagement/blob/main/ProjectBudget.xltx
Communication plan | Details of the communication schedule and frequency. Link - https://github.com/bhaumikananda/GoogleProjectManagement/blob/main/AB_Activity-Template_-Comm-plan.xlsx
Shared folder | Documentation link.
RACI chart | Team RACI structure - https://github.com/bhaumikananda/GoogleProjectManagement/blob/main/RACI-Chart---Phase-2.xlsx

## Project Schedule
Gantt Chart
TITLE: Plant Pals Operations and Training Plan | [6 empty] | COMPANY NAME: |  |  |  |  | Office Green
PROJECT MANAGER: [Name] | [6 empty] | CREATION DATE: |  |  |  |  | 02/15
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Establish a plant delivery and logistics plan | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Source packaging materials | Fulfillment Director | 3/1 | 3/12 | 10 | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | Hire delivery drivers | Human Resources Specialist | 3/15 | 3/26 | 10 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Calculate the delivery fees | Financial Analyst | 3/29 | 4/9 | 10 | 0% | bar: MARCH M 29 to APRIL F 9
2 | Select and install supply chain software and equipment
2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory Manager | 4/12 | 4/14 | 3 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Supervise vendor installation of the fulfillment equipment | Fulfillment Director | 4/15 | 4/16 | 2 | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Determine internal safety protocols for the equipment | Quality Assurance Tester | 4/19 | 4/30 | 10 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Develop and launch an employee training program
3.1 | Develop training sessions | Human Resources Specialist | 5/3 | 5/14 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Train employees to use the software and equipment | Training Manager | 5/17 | 5/28 | 10 | 0% | bar: MAY M 17 to MAY F 28
3.3 | Monitor employee progress and improve training processes | Training Manager | 5/31 | 6/11 | 10 | 0% | bar: MAY M 31 to JUNE F 11

## Budget
Create Website Budget in this worksheet. Helpful instructions on how to use this worksheet are in cells in this column. Arrow down to get started.
Enter Company Name in cell at right. | Company Name
Title of this worksheet is in cell at right. | Web Site Budgeting Tool
Enter Date in cell at right. | Date
Tip is in cell at right. | Gray cells contain calculations that should not be altered.
Enter details in Rate table starting in cell at right. Next instruction is in cell A10. | Company Data | Rate
| Required rate of return | 10%
| Tax rate | 30%
Enter details in Initial Invest table starting in cell at right. Next instruction is in cell A16. | Initial Investment in Web Site | YEAR | 1 | 2 | 3
| Hardware (e.g., servers) | 25000
| Software (e.g., e-commerce catalog software) | 15000
| Development (e.g., third-party site design and development) | 150000
| Total Initial Investments | 190000
Enter details in Benefits table starting in cell at right. Next instruction is in cell A24. | Benefits from Web Site | YEAR | 1 | 2 | 3
| Direct sales |  | 15000 | 50000 | 75000
| Incremental sales resulting from enhanced promotional/salesperson effectiveness |  | 25000 | 25000 | 25000
| Incremental sales resulting from increased partner participation |  | 25000 | 25000 | 25000
| Reduced travel costs |  | 25000 | 25000 | 25000
| Reduced customer service costs |  | 50000 | 50000 | 50000
| Total Benefits |  | 140000 | 175000 | 200000
Enter details in Costs table starting in cell at right. Values are auto calculated in cells containing formulae. Next instruction is in cell A32. | Costs (Excluding Initial Capital Investments) | YEAR | 1 | 2 | 3
| Cost of sales |  | 7500 | 25000 | 37500
| Maintenance |  | 15000 | 15000 | 15000
| Project management, customer support |  | 35000 | 35000 | 35000
| Online advertising, search-engine registration |  | 10000 | 10000 | 10000
| Depreciation on capital expenditures (calculation uses three-year period) |  | 63333.3333 | 63333.3333 | 63333.3333
| Total Costs |  | 130833.3333 | 148333.3333 | 160833.3333
Values are auto calculated in Totals table starting in cell at right. Next instruction is in cell A49. | Totals | YEAR | 1 | 2 | 3
| Net Benefits (Costs) |  | 9166.6667 | 26666.6667 | 39166.6667
| Tax |  | 2750 | 8000 | 11750
| Value after tax |  | 6416.6667 | 18666.6667 | 27416.6667
| Depreciation added back |  | 63333.3333 | 63333.3333 | 63333.3333
| Cash flow | -190000 | 69750 | 82000 | 90750
| Cumulative cash flow | -190000 | -120250 | -38250 | 52500
Evaluation Metrics are auto calculated in Metrics table starting in cell at right. | Evaluation Metrics | Values
| Net present value (NPV) | 9359.5041
| Internal rate of return (IRR) | 12.66%
| Payback period (in years) | 2.4215

## Communication Plan
Project Plant Pals: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings.
Software and Equipment Vendor | Survey | One time | Core Team: HR Specialist & Training Manager | Before end of SoW | In Person | Ask questions about the new software and equipment to create an effective training plan for Office Green's employees
Human Resources | Planning Check-In | Weekly | Core Team: HR Specialist | Every Monday | Phone Call | Project planning assistance; provide support during the training session |  | On special need there will be additional meetings
Facilities | Informational Update | One time | Core Team: Administrative Coordinator | During the first week of schedule preparation | Email (from individual address) | Reserve rooms, spaces, and equipment needed for employee training |  | For any change, adhoc communication will be sent to inform about the changes
Print Shop | Planning Meeting | One time | Core Team: Administrative Coordinator | During the first week of schedule preparation the requirement of copies should be sent out. | In Person | Coordinate on the printing and delivery of training manuals for employees |  | For ant change required as part of survery or process improvement there might be additional meetings required
Office Green employees | Informational Update | One time | Core Team: Training Manager | During the first week of schedule preparation | Email (from individual address) | Communicate schedules, locations, and other necessary details to trainees
Office Green employees | Training | Daily | Core Team: Training Manager | Daily start at 9:00 am | In Person | Train employees to use the supply chain management software and equipment
Office Green employees | Survey | One time | Core Team: Training Manager | Post training | Email (from company address) | Post-training survey
Your Manager | Status Update | Weekly | Project Manager | Every Monday at 12:00 PM | Phone Call | Update on event planning, ask questions, and get feedback
Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | Weekly | Project Manager | Every Monday at 1:00 PM | Email (from individual address) | High-level information and general updates